## Notes
Gantt Chart | Example | Description
GC1 | Protocol only (Abbreviated protocol) - daily | This is only for the protocol stage; very basic, without much iterations or scoping
GC2 | Protocol + 1 review - daily | This has an example of a protocol and the corresponding review. In this example, the "work" on the review started as soon as the final details are confirmed
GC3 | Protocol + multiple reviews - daily | As above, but showed that the "search and screen" tasks can be done for all reviews at one go. Number of reviews can be added by "copy and pasting" the "Review" rows. Actual start dates will depend on the author availability etc
GC4 | Protocol + 1 review (weekly) | This is more suitable for reviews that will take over a year, or complex review
Other Notes:
Leave dates | I have created a section which we can enter public holidays and author's main leave where the projects need to pause. The formula I used for calculating end dates take into account weekends, public holidays and author's leaves. We can modify to be simpler - i.e. ignoring public holidays and Saturdays/Sundays if this is actually where progress in made in Cochrane reviews.
Start date | Only need to fill in the start date of the first task in each work segment. By default, the start date will be the day after completing the previous task
Start date - yellow cells | These are the cells which were manually entered - The "start date" of the tasks is before the end of the "finish date" of the previous tasks, because there are tasks where we can begin concurrently or before the previous one had ended
CRG | These "durations" are very much dependent on the CRG processes to remind authors this is where they need to liase with the editorial groups and probably set some agreed target dates

## GC1-Protocol only
Task ID | Task | Responsible | Duration | Start date | Finish date | Status | 2019-01-01 | [30 empty] | 2019-02-01 | [27 empty] | 2019-03-01 | [30 empty] | 2019-04-01 | [29 empty] | 2019-05-01 | [30 empty] | 2019-06-01 | [29 empty] | 2019-07-01 | [30 empty] | 2019-08-01 | [30 empty] | 2019-09-01 | [29 empty] | october | [30 empty] | 2019-11-01 | [29 empty] | 2019-12-01
 | time axis 2019-01-01 to 2019-12-31
Review Title | time axis 2019-01-01 to 2019-12-31
| Start date protocol | 2019-01-01
| End date Protocol | 2019-07-01
| Start date review | #REF!
| End date Review | #REF!
Leave planning - for dates authors are unavailable, on leave or away, mark "X" on the affected dates
First author (A1) | bar: 2019-01-01 to 2019-01-08
2nd author (A2) on leave/ not available
Clinical author1 (CA1) on leave/ not available
Clinical author2 (CA2) on leave/ not available
PROTOCOL (abbreviated version) |  |  |  | 2019-01-01 | 2019-07-01
Started
P | TELECON (ALL) - Initial scope of review(s) | AT | 1 | 2019-01-01 | 2019-01-08
P | Scoping PICO & analysis methods |  | 10 | 2019-01-09 | 2019-01-22
P | Confirmation PICO |  | 3 | 2019-01-23 | 2019-01-27
P | Drafting Protocol |  | 4 | 2019-01-23 | 2019-01-28
P | Initial Draft circulated |  | 1 | 2019-01-29 | 2019-01-29
P | Comments/feedback on initial draft |  | 5 | 2019-01-30 | 2019-02-05
P | TELECON (ALL) - Discussions of protocol | AT | 1 | 2019-02-06 | 2019-02-06
P | Revise draft protocol |  | 5 | 2019-02-07 | 2019-02-13
P | Circulate and comment on revised draft |  | 10 | 2019-02-14 | 2019-02-27
P | Final draft agreed |  | 5 | 2019-02-28 | 2019-03-06
P | Data extraction forms finalised |  | 5 | 2019-02-28 | 2019-03-06
P | Submit to Editorial group | FA | 1 | 2019-03-07 | 2019-03-07
P | Copy editing | CRG | 5 | 2019-03-08 | 2019-03-14
P | Initial Editorial feedback |  | 2 | 2019-03-15 | 2019-03-18
P | Edit and resubmit |  | 5 | 2019-03-19 | 2019-03-25
P | Submit for external peer review | CRG | 15 | 2019-03-26 | 2019-04-15
P | External Peer review |  | 5 | 2019-04-16 | 2019-04-24
P | Review comments and respond to peer reviewers |  | 5 | 2019-04-25 | 2019-05-01
P | Review comments and respond to peer reviewers (clinical) |  | 5 | 2019-04-25 | 2019-05-01
P | TELECON (ALL) - Peer review comments | AT | 1 | 2019-05-02 | 2019-05-02
P | Finalise and resubmit for editorial approval | FA | 3 | 2019-05-03 | 2019-05-08
P | Editorial review | CRG | 10 | 2019-05-09 | 2019-05-22
P | Review comments and respond to editors | AT | 5 | 2019-05-23 | 2019-05-30
P | Final submssion | AT | 2 | 2019-05-31 | 2019-06-03
P | Final copy editing & editorial process | CRG | 5 | 2019-06-04 | 2019-06-10
P | Publish | CRG | 15 | 2019-06-11 | 2019-07-01
134

## GC2-Protocol + 1 review
Task ID | Task | Responsible | Duration | Start date | Finish date | Status | 2019-01-01 | [30 empty] | 2019-02-01 | [27 empty] | 2019-03-01 | [30 empty] | 2019-04-01 | [29 empty] | 2019-05-01 | [30 empty] | 2019-06-01 | [29 empty] | 2019-07-01 | [30 empty] | 2019-08-01 | [30 empty] | 2019-09-01 | [29 empty] | october | [30 empty] | 2019-11-01 | [29 empty] | 2019-12-01
 | time axis 2019-01-01 to 2019-12-31
Review Title | time axis 2019-01-01 to 2019-12-31
| Start date protocol | 2019-01-01
| End date Protocol | 2019-07-01
| Start date review | 2019-06-03
| End date Review | 2020-01-30
Leave planning - for dates authors are unavailable, on leave or away, mark "X" on the affected dates
First author (A1) | bar: 2019-01-01 to 2019-01-08
2nd author (A2) on leave/ not available
Clinical author1 (CA1) on leave/ not available
Clinical author2 (CA2) on leave/ not available
PROTOCOL (abbreviated version) |  |  |  | 2019-01-01 | 2019-07-01
Started
P | TELECON (ALL) - Initial scope of review(s) | AT | 1 | 2019-01-01 | 2019-01-08
P | Scoping PICO & analysis methods |  | 10 | 2019-01-09 | 2019-01-22
P | Confirmation PICO |  | 3 | 2019-01-23 | 2019-01-27
P | Drafting Protocol |  | 4 | 2019-01-23 | 2019-01-28
P | Initial Draft circulated |  | 1 | 2019-01-29 | 2019-01-29
P | Comments/feedback on initial draft |  | 5 | 2019-01-30 | 2019-02-05
P | TELECON (ALL) - Discussions of protocol | AT | 1 | 2019-02-06 | 2019-02-06
P | Revise draft protocol |  | 5 | 2019-02-07 | 2019-02-13
P | Circulate and comment on revised draft |  | 10 | 2019-02-14 | 2019-02-27
P | Final draft agreed |  | 5 | 2019-02-28 | 2019-03-06
P | Data extraction forms finalised |  | 5 | 2019-02-28 | 2019-03-06
P | Submit to Editorial group | FA | 1 | 2019-03-07 | 2019-03-07
P | Copy editing | CRG | 5 | 2019-03-08 | 2019-03-14
P | Initial Editorial feedback |  | 2 | 2019-03-15 | 2019-03-18
P | Edit and resubmit |  | 5 | 2019-03-19 | 2019-03-25
P | Submit for external peer review | CRG | 15 | 2019-03-26 | 2019-04-15
P | External Peer review |  | 5 | 2019-04-16 | 2019-04-24
P | Review comments and respond to peer reviewers |  | 5 | 2019-04-25 | 2019-05-01
P | Review comments and respond to peer reviewers (clinical) |  | 5 | 2019-04-25 | 2019-05-01
P | TELECON (ALL) - Peer review comments | AT | 1 | 2019-05-02 | 2019-05-02
P | Finalise and resubmit for editorial approval | FA | 3 | 2019-05-03 | 2019-05-08
P | Editorial review | CRG | 10 | 2019-05-09 | 2019-05-22
P | Review comments and respond to editors | AT | 5 | 2019-05-23 | 2019-05-30
P | Final submssion | AT | 2 | 2019-05-31 | 2019-06-03
P | Final copy editing & editorial process | CRG | 5 | 2019-06-04 | 2019-06-10
P | Publish | CRG | 15 | 2019-06-11 | 2019-07-01
134
ALL REVIEWS (IF doing a series of reviews)
Search and screen |  |  |  | 2019-03-07 | 2019-01-09
S1 | Run search |  |  | 2019-03-07 | 2019-03-06
S2 | Screening abstracts |  |  | 2019-01-02 | 2019-01-01
S3 | Resolve discrepancy |  |  | 2019-01-03 | 2019-01-02
S4 | Obtain full papers |  |  | 2019-01-04 | 2019-01-03
S5 | Arrange for translations of papers |  |  | 2019-01-05 | 2019-01-04
S6 | Screen full papers |  |  | 2019-01-06 | 2019-01-05
S7 | Screen full papers |  |  | 2019-01-07 | 2019-01-06
S8 | Resolve discprepancy - methodological |  |  | 2019-01-08 | 2019-01-07
S9 | Resolve discprepancy - clinical |  |  | 2019-01-09 | 2019-01-08
S10 | Confim list of included papers |  |  | 2019-01-10 | 2019-01-09
REVIEW 1 |  |  |  | 2019-06-03 | 2020-01-30
Seach and screen |  | Time(weeks) | 5 | 2019-06-03 | 2019-07-08
S1 | Run search |  | 5 | 2019-06-03 | 2019-06-09
S2 | Screening abstracts |  | 3 | 2019-06-10 | 2019-06-12
S3 | Resolve discrepancy |  | 3 | 2019-06-13 | 2019-06-17
S4 | Obtain full papers |  | 5 | 2019-06-18 | 2019-06-24
S5 | Arrange for translations of papers |  | 15 | 2019-06-18 | 2019-07-08
S6 | Screen full papers 1 |  | 5 | 2019-06-19 | 2019-06-25
S7 | Screen full papers 2 |  | 5 | 2019-06-19 | 2019-06-25
S8 | Resolve discprepancy - methodological |  | 5 | 2019-06-25 | 2019-07-01
S9 | Resolve discprepancy - clinical |  | 5 | 2019-06-25 | 2019-07-01
S10 | Confirm list of included papers |  | 5 | 2019-07-02 | 2019-07-08
Data extraction and analysis |  | Time(weeks) | 8 | 2019-06-25 | 2019-08-20
D1 | Data extraction 1 |  | 15 | 2019-06-25 | 2019-07-15
D2 | Data extraction 2 |  | 15 | 2019-06-25 | 2019-07-15
D3 | Resolve discprepancy - methodological |  | 10 | 2019-07-16 | 2019-07-29
D4 | Resolve discprepancy - clinical |  | 10 | 2019-07-16 | 2019-07-29
D5 | Data extraction - finalised and merged |  | 10 | 2019-07-16 | 2019-07-29
D6 | Data entry into RevMan |  | 5 | 2019-07-30 | 2019-08-05
D7 | Analysis |  | 5 | 2019-08-06 | 2019-08-12
D8 | Analysis check |  | 5 | 2019-08-13 | 2019-08-19
D9 | Doing SOF |  | 5 | 2019-08-13 | 2019-08-19
D10/T1 | TELECON (ALL) - Agree on analysis, intepretation and key points |  | 1 | 2019-08-20 | 2019-08-20
Write up |  | Time(weeks) | 9.7143 | 2019-07-30 | 2019-10-06
W1 | Write up - ROB, included studies |  | 5 | 2019-07-30 | 2019-08-05
W2 | Write up - Effects of intervention, Research implications, Abstracts, PLS |  | 5 | 2019-08-20 | 2019-08-26
W3 | Write up - Discussions, Implications for practice |  | 5 | 2019-08-27 | 2019-09-02
W4 | Review first drafts and putting together initial draft |  | 5 | 2019-09-03 | 2019-09-09
W5 | Cirulate drafts - comments and feedback | AT | 5 | 2019-09-10 | 2019-09-16
W6 | Review/summarise comments |  | 3 | 2019-09-17 | 2019-09-19
W7/T2 | TELECON (ALL) - Discussions of draft | AT | 1 | 2019-09-20 | 2019-09-22
W8 | Revise drafts |  | 5 | 2019-09-23 | 2019-09-29
W9 | Cirulate drafts - comments and feedback |  | 5 | 2019-09-30 | 2019-10-06
W10 | Revise drafts |  | 5 | 2019-09-30 | 2019-10-06
Peer reviewing |  | Time(weeks) | 10.2857 | 2019-09-30 | 2019-12-11
PR1 | Submit for external peer review |  | 2 | 2019-09-30 | 2019-10-01
PR2 | External Peer review | CRG | 15 | 2019-10-02 | 2019-10-22
PR3 | Review comments and respond to peer reviewers |  | 7 | 2019-10-23 | 2019-10-31
PR4 | Review comments and respond to peer reviewers (clinical) |  | 7 | 2019-11-01 | 2019-11-11
PR5/T3 | TELECON (ALL) - Peer review comments |  | 1 | 2019-11-12 | 2019-11-12
PR6 | Finalise and resubmit for editorial approval |  | 5 | 2019-11-13 | 2019-11-19
PR7 | Editorial review | CRG | 10 | 2019-11-20 | 2019-12-03
PR8 | Review comments and respond to editors |  | 5 | 2019-12-04 | 2019-12-10
PR9 | Review comments and respond to editors (clinical) |  | 5 | 2019-12-04 | 2019-12-10
PR10/T4 | TELECON (ALL) - Editorial comments | AT | 1 | 2019-12-11 | 2019-12-11
Editorial process and publications |  | Time(weeks) | 7 | 2019-12-12 | 2020-01-30
E1 | Submission of final draft |  | 2 | 2019-12-12 | 2019-12-15
E2 | Copy editing of final draft | CRG | 10 | 2019-12-16 | 2019-12-29
E3 | Editorial sign off | CRG | 5 | 2019-12-30 | 2020-01-05
E4 | CEU screening | CRG | 14 | 2020-01-06 | 2020-01-23
E5 | Publication | CRG | 5 | 2020-01-24 | 2020-01-30

## GC3-Protocol + multiple review3
Task ID | Task | Responsible | Duration | Start date | Finish date | Status | 2019-01-01 | [30 empty] | 2019-02-01 | [27 empty] | 2019-03-01 | [30 empty] | 2019-04-01 | [29 empty] | 2019-05-01 | [30 empty] | 2019-06-01 | [29 empty] | 2019-07-01 | [30 empty] | 2019-08-01 | [30 empty] | 2019-09-01 | [29 empty] | october | [30 empty] | 2019-11-01 | [29 empty] | 2019-12-01
 | time axis 2019-01-01 to 2019-12-31
Review Title | time axis 2019-01-01 to 2019-12-31
| Start date protocol | 2019-01-01
| End date Protocol | 2019-07-01
| Start date review | 2019-04-10
| End date Review | 2019-11-21
Leave planning - for dates authors are unavailable, on leave or away, mark "X" on the affected dates
First author (A1) | bar: 2019-01-01 to 2019-01-08
2nd author (A2) on leave/ not available
Clinical author1 (CA1) on leave/ not available
Clinical author2 (CA2) on leave/ not available
PROTOCOL (abbreviated version) |  |  |  | 2019-01-01 | 2019-07-01
Started
P | TELECON (ALL) - Initial scope of review(s) | AT | 1 | 2019-01-01 | 2019-01-08
P | Scoping PICO & analysis methods |  | 10 | 2019-01-09 | 2019-01-22
P | Confirmation PICO |  | 3 | 2019-01-23 | 2019-01-27
P | Drafting Protocol |  | 4 | 2019-01-23 | 2019-01-28
P | Initial Draft circulated |  | 1 | 2019-01-29 | 2019-01-29
P | Comments/feedback on initial draft |  | 5 | 2019-01-30 | 2019-02-05
P | TELECON (ALL) - Discussions of protocol | AT | 1 | 2019-02-06 | 2019-02-06
P | Revise draft protocol |  | 5 | 2019-02-07 | 2019-02-13
P | Circulate and comment on revised draft |  | 10 | 2019-02-14 | 2019-02-27
P | Final draft agreed |  | 5 | 2019-02-28 | 2019-03-06
P | Data extraction forms finalised |  | 5 | 2019-02-28 | 2019-03-06
P | Submit to Editorial group | FA | 1 | 2019-03-07 | 2019-03-07
P | Copy editing | CRG | 5 | 2019-03-08 | 2019-03-14
P | Initial Editorial feedback |  | 2 | 2019-03-15 | 2019-03-18
P | Edit and resubmit |  | 5 | 2019-03-19 | 2019-03-25
P | Submit for external peer review | CRG | 15 | 2019-03-26 | 2019-04-15
P | External Peer review |  | 5 | 2019-04-16 | 2019-04-24
P | Review comments and respond to peer reviewers |  | 5 | 2019-04-25 | 2019-05-01
P | Review comments and respond to peer reviewers (clinical) |  | 5 | 2019-04-25 | 2019-05-01
P | TELECON (ALL) - Peer review comments | AT | 1 | 2019-05-02 | 2019-05-02
P | Finalise and resubmit for editorial approval | FA | 3 | 2019-05-03 | 2019-05-08
P | Editorial review | CRG | 10 | 2019-05-09 | 2019-05-22
P | Review comments and respond to editors | AT | 5 | 2019-05-23 | 2019-05-30
P | Final submssion | AT | 2 | 2019-05-31 | 2019-06-03
P | Final copy editing & editorial process | CRG | 5 | 2019-06-04 | 2019-06-10
P | Publish | CRG | 15 | 2019-06-11 | 2019-07-01
| Total work days |  | 134
ALL REVIEWS (IF doing a series of reviews)
Search and screen |  | Time(weeks) | 5 | 2019-03-06 | 2019-04-10
S1 | Run search |  | 5 | 2019-03-06 | 2019-03-12
S2 | Screening abstracts |  | 3 | 2019-03-13 | 2019-03-17
S3 | Resolve discrepancy |  | 3 | 2019-03-18 | 2019-03-20
S4 | Obtain full papers |  | 5 | 2019-03-21 | 2019-03-27
S5 | Arrange for translations of papers |  | 15 | 2019-03-21 | 2019-04-10
S6 | Screen full papers 1 |  | 5 | 2019-03-22 | 2019-03-28
S7 | Screen full papers 2 |  | 5 | 2019-03-22 | 2019-03-28
S8 | Resolve discprepancy - methodological |  | 5 | 2019-03-28 | 2019-04-03
S9 | Resolve discprepancy - clinical |  | 5 | 2019-03-28 | 2019-04-03
S10 | Confirm list of included papers |  | 5 | 2019-04-04 | 2019-04-10
REVIEW 1 |  |  |  | 2019-04-10 | 2019-11-21
Data extraction and analysis |  | Time(weeks) | 8.8571 | 2019-04-10 | 2019-06-11
D1 | Data extraction 1 |  | 15 | 2019-04-10 | 2019-05-02
D2 | Data extraction 2 |  | 15 | 2019-04-10 | 2019-05-02
D3 | Resolve discprepancy - methodological |  | 10 | 2019-05-03 | 2019-05-19
D4 | Resolve discprepancy - clinical |  | 10 | 2019-05-03 | 2019-05-19
D5 | Data extraction - finalised and merged |  | 10 | 2019-05-03 | 2019-05-19
D6 | Data entry into RevMan |  | 5 | 2019-05-20 | 2019-05-27
D7 | Analysis |  | 5 | 2019-05-28 | 2019-06-03
D8 | Analysis check |  | 5 | 2019-06-04 | 2019-06-10
D9 | Doing SOF |  | 5 | 2019-06-04 | 2019-06-10
D10/T1 | TELECON (ALL) - Agree on analysis, intepretation and key points |  | 1 | 2019-06-11 | 2019-06-11
Write up |  | Time(weeks) | 9.8571 | 2019-05-20 | 2019-07-28
W1 | Write up - ROB, included studies |  | 5 | 2019-05-20 | 2019-05-27
W2 | Write up - Effects of intervention, Research implications, Abstracts, PLS |  | 5 | 2019-06-11 | 2019-06-17
W3 | Write up - Discussions, Implications for practice |  | 5 | 2019-06-18 | 2019-06-24
W4 | Review first drafts and putting together initial draft |  | 5 | 2019-06-25 | 2019-07-01
W5 | Cirulate drafts - comments and feedback | AT | 5 | 2019-07-02 | 2019-07-08
W6 | Review/summarise comments |  | 3 | 2019-07-09 | 2019-07-11
W7/T2 | TELECON (ALL) - Discussions of draft | AT | 1 | 2019-07-12 | 2019-07-14
W8 | Revise drafts |  | 5 | 2019-07-15 | 2019-07-21
W9 | Cirulate drafts - comments and feedback |  | 5 | 2019-07-22 | 2019-07-28
W10 | Revise drafts |  | 5 | 2019-07-22 | 2019-07-28
Peer reviewing |  | Time(weeks) | 10.2857 | 2019-07-22 | 2019-10-02
PR1 | Submit for external peer review |  | 2 | 2019-07-22 | 2019-07-23
PR2 | External Peer review | CRG | 15 | 2019-07-24 | 2019-08-13
PR3 | Review comments and respond to peer reviewers |  | 7 | 2019-08-14 | 2019-08-22
PR4 | Review comments and respond to peer reviewers (clinical) |  | 7 | 2019-08-23 | 2019-09-02
PR5/T3 | TELECON (ALL) - Peer review comments |  | 1 | 2019-09-03 | 2019-09-03
PR6 | Finalise and resubmit for editorial approval |  | 5 | 2019-09-04 | 2019-09-10
PR7 | Editorial review | CRG | 10 | 2019-09-11 | 2019-09-24
PR8 | Review comments and respond to editors |  | 5 | 2019-09-25 | 2019-10-01
PR9 | Review comments and respond to editors (clinical) |  | 5 | 2019-09-25 | 2019-10-01
PR10/T4 | TELECON (ALL) - Editorial comments | AT | 1 | 2019-10-02 | 2019-10-02
Editorial process and publications |  | Time(weeks) | 7 | 2019-10-03 | 2019-11-21
E1 | Submission of final draft |  | 2 | 2019-10-03 | 2019-10-06
E2 | Copy editing of final draft | CRG | 10 | 2019-10-07 | 2019-10-20
E3 | Editorial sign off | CRG | 5 | 2019-10-21 | 2019-10-27
E4 | CEU screening | CRG | 14 | 2019-10-28 | 2019-11-14
E5 | Publication | CRG | 5 | 2019-11-15 | 2019-11-21
REVIEW 2 |  |  |  | 2019-03-06 | 2019-12-05
Seach and screen |  | Time(weeks) | 5 | 2019-03-06 | 2019-04-10
S1 | Run search |  | 5 | 2019-03-06 | 2019-03-12
S2 | Screening abstracts |  | 3 | 2019-03-13 | 2019-03-17
S3 | Resolve discrepancy |  | 3 | 2019-03-18 | 2019-03-20
S4 | Obtain full papers |  | 5 | 2019-03-21 | 2019-03-27
S5 | Arrange for translations of papers |  | 15 | 2019-03-21 | 2019-04-10
S6 | Screen full papers 1 |  | 5 | 2019-03-22 | 2019-03-28
S7 | Screen full papers 2 |  | 5 | 2019-03-22 | 2019-03-28
S8 | Resolve discprepancy - methodological |  | 5 | 2019-03-28 | 2019-04-03
S9 | Resolve discprepancy - clinical |  | 5 | 2019-03-28 | 2019-04-03
S10 | Confirm list of included papers |  | 5 | 2019-04-04 | 2019-04-10
Data extraction and analysis |  | Time(weeks) | 10.8571 | 2019-04-10 | 2019-06-25
D1 | Data extraction 1 |  | 15 | 2019-04-10 | 2019-05-02
D2 | Data extraction 2 |  | 15 | 2019-04-10 | 2019-05-02
D3 | Resolve discprepancy - methodological |  | 10 | 2019-05-03 | 2019-05-19
D4 | Resolve discprepancy - clinical |  | 10 | 2019-05-03 | 2019-05-19
D5 | Data extraction - finalised and merged |  | 10 | 2019-05-03 | 2019-05-19
D6 | Data entry into RevMan |  | 5 | 2019-05-20 | 2019-05-27
D7 | Analysis |  | 5 | 2019-06-11 | 2019-06-17
D8 | Analysis check |  | 5 | 2019-06-18 | 2019-06-24
D9 | Doing SOF |  | 5 | 2019-06-18 | 2019-06-24
D10/T1 | TELECON (ALL) - Agree on analysis, intepretation and key points |  | 1 | 2019-06-25 | 2019-06-25
Write up |  | Time(weeks) | 11.8571 | 2019-05-20 | 2019-08-11
W1 | Write up - ROB, included studies |  | 5 | 2019-05-20 | 2019-05-27
W2 | Write up - Effects of intervention, Research implications, Abstracts, PLS |  | 5 | 2019-06-25 | 2019-07-01
W3 | Write up - Discussions, Implications for practice |  | 5 | 2019-07-02 | 2019-07-08
W4 | Review first drafts and putting together initial draft |  | 5 | 2019-07-09 | 2019-07-15
W5 | Cirulate drafts - comments and feedback | AT | 5 | 2019-07-16 | 2019-07-22
W6 | Review/summarise comments |  | 3 | 2019-07-23 | 2019-07-25
W7/T2 | TELECON (ALL) - Discussions of draft | AT | 1 | 2019-07-26 | 2019-07-28
W8 | Revise drafts |  | 5 | 2019-07-29 | 2019-08-04
W9 | Cirulate drafts - comments and feedback |  | 5 | 2019-08-05 | 2019-08-11
W10 | Revise drafts |  | 5 | 2019-08-05 | 2019-08-11
Peer reviewing |  | Time(weeks) | 10.2857 | 2019-08-05 | 2019-10-16
PR1 | Submit for external peer review |  | 2 | 2019-08-05 | 2019-08-06
PR2 | External Peer review | CRG | 15 | 2019-08-07 | 2019-08-27
PR3 | Review comments and respond to peer reviewers |  | 7 | 2019-08-28 | 2019-09-05
PR4 | Review comments and respond to peer reviewers (clinical) |  | 7 | 2019-09-06 | 2019-09-16
PR5/T3 | TELECON (ALL) - Peer review comments |  | 1 | 2019-09-17 | 2019-09-17
PR6 | Finalise and resubmit for editorial approval |  | 5 | 2019-09-18 | 2019-09-24
PR7 | Editorial review | CRG | 10 | 2019-09-25 | 2019-10-08
PR8 | Review comments and respond to editors |  | 5 | 2019-10-09 | 2019-10-15
PR9 | Review comments and respond to editors (clinical) |  | 5 | 2019-10-09 | 2019-10-15
PR10/T4 | TELECON (ALL) - Editorial comments | AT | 1 | 2019-10-16 | 2019-10-16
Editorial process and publications |  | Time(weeks) | 7 | 2019-10-17 | 2019-12-05
E1 | Submission of final draft |  | 2 | 2019-10-17 | 2019-10-20
E2 | Copy editing of final draft | CRG | 10 | 2019-10-21 | 2019-11-03
E3 | Editorial sign off | CRG | 5 | 2019-11-04 | 2019-11-10
E4 | CEU screening | CRG | 14 | 2019-11-11 | 2019-11-28
E5 | Publication | CRG | 5 | 2019-11-29 | 2019-12-05
For this review - I did not take out the search and screen rows, only hiding them. I started the data extractions together with Review 1, but only started analysis after Review 1
For this example - I took out the search and screen rows, since this can be done across a few reviews

## GC4 - weekly
Task ID | Task | Who | Duration | Start date | Finish date | Status
[6 empty] | Date | 2019-01-01 | 2019-01-08 | 2019-01-15 | 2019-01-22 | 2019-01-29 | 2019-02-05 | 2019-02-12 | 2019-02-19 | 2019-02-26 | 2019-03-05 | 2019-03-12 | 2019-03-19 | 2019-03-26 | 2019-04-02 | 2019-04-09 | 2019-04-16 | 2019-04-23 | 2019-04-30 | 2019-05-07 | 2019-05-14 | 2019-05-21 | 2019-05-28 | 2019-06-04 | 2019-06-11 | 2019-06-18 | 2019-06-25 | 2019-07-02 | 2019-07-09 | 2019-07-16 | 2019-07-23 | 2019-07-30 | 2019-08-06 | 2019-08-13 | 2019-08-20 | 2019-08-27 | 2019-09-03 | 2019-09-10 | 2019-09-17 | 2019-09-24 | 2019-10-01 | 2019-10-08 | 2019-10-15 | 2019-10-22 | 2019-10-29 | 2019-11-05 | 2019-11-12 | 2019-11-19 | 2019-11-26 | 2019-12-03 | 2019-12-10 | 2019-12-17 | 2019-12-24 | 2019-12-31 | 2020-01-07 | 2020-01-14 | 2020-01-21 | 2020-01-28 | 2020-02-04 | 2020-02-11 | 2020-02-18 | 2020-02-25 | 2020-03-03 | 2020-03-10 | 2020-03-17 | 2020-03-24 | 2020-03-31 | 2020-04-07 | 2020-04-14 | 2020-04-21 | 2020-04-28 | 2020-05-05 | 2020-05-12 | 2020-05-19 | 2020-05-26 | 2020-06-02 | 2020-06-09 | 2020-06-16 | 2020-06-23 | 2020-06-30 | 2020-07-07 | 2020-07-14 | 2020-07-21 | 2020-07-28 | 2020-08-04 | 2020-08-11 | 2020-08-18 | 2020-08-25 | 2020-09-01 | 2020-09-08 | 2020-09-15 | 2020-09-22 | 2020-09-29 | 2020-10-06 | 2020-10-13 | 2020-10-20 | 2020-10-27 | 2020-11-03 | 2020-11-10 | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2020-12-15 | 2020-12-22 | 2020-12-29 | 2021-01-05 | 2021-01-12 | 2021-01-19 | 2021-01-26 | 2021-02-02 | 2021-02-09 | 2021-02-16 | 2021-02-23 | 2021-03-02 | 2021-03-09 | 2021-03-16 | 2021-03-23 | 2021-03-30 | 2021-04-06 | 2021-04-13 | 2021-04-20 | 2021-04-27 | 2021-05-04 | 2021-05-11 | 2021-05-18 | 2021-05-25 | 2021-06-01
| Review/project name |  |  |  |  | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127
| Start date protocol | 2019-01-01
| End date Protocol | 2019-07-01
| Start date review | 2019-06-03
| End date Review | 2020-01-30
Leave planning - for dates authors are unavailable, on leave or away, mark "X" on the affected dates
| First author (A1) | [5 empty] | x
2nd author (A2) on leave/ not available
Clinical author1 (CA1) on leave/ not available
Clinical author2 (CA2) on leave/ not available
PROTOCOL (abbreviated version) |  |  |  | 2019-01-01 | 2019-07-01
Started
P | TELECON (ALL) - Initial scope of review(s) | AT | 1 | 2019-01-01 | 2019-01-08
P | Scoping PICO & analysis methods |  | 10 | 2019-01-09 | 2019-01-22
P | Confirmation PICO |  | 3 | 2019-01-23 | 2019-01-27
P | Drafting Protocol |  | 4 | 2019-01-23 | 2019-01-28
P | Initial Draft circulated |  | 1 | 2019-01-29 | 2019-01-29
P | Comments/feedback on initial draft |  | 5 | 2019-01-30 | 2019-02-05
P | TELECON (ALL) - Discussions of protocol | AT | 1 | 2019-02-06 | 2019-02-06
P | Revise draft protocol |  | 5 | 2019-02-07 | 2019-02-13
P | Circulate and comment on revised draft |  | 10 | 2019-02-14 | 2019-02-27
P | Final draft agreed |  | 5 | 2019-02-28 | 2019-03-06
P | Data extraction forms finalised |  | 5 | 2019-02-28 | 2019-03-06
P | Submit to Editorial group | FA | 1 | 2019-03-07 | 2019-03-07
P | Copy editing | CRG | 5 | 2019-03-08 | 2019-03-14
P | Initial Editorial feedback |  | 2 | 2019-03-15 | 2019-03-18
P | Edit and resubmit |  | 5 | 2019-03-19 | 2019-03-25
P | Submit for external peer review | CRG | 15 | 2019-03-26 | 2019-04-15
P | External Peer review |  | 5 | 2019-04-16 | 2019-04-24
P | Review comments and respond to peer reviewers |  | 5 | 2019-04-25 | 2019-05-01
P | Review comments and respond to peer reviewers (clinical) |  | 5 | 2019-04-25 | 2019-05-01
P | TELECON (ALL) - Peer review comments | AT | 1 | 2019-05-02 | 2019-05-02
P | Finalise and resubmit for editorial approval | FA | 3 | 2019-05-03 | 2019-05-08
P | Editorial review | CRG | 10 | 2019-05-09 | 2019-05-22
P | Review comments and respond to editors | AT | 5 | 2019-05-23 | 2019-05-30
P | Final submssion | AT | 2 | 2019-05-31 | 2019-06-03
P | Final copy editing & editorial process | CRG | 5 | 2019-06-04 | 2019-06-10
P | Publish | CRG | 15 | 2019-06-11 | 2019-07-01
134
ALL REVIEWS (IF doing a series of reviews)
Search and screen |  |  |  | 2019-03-07 | 2019-01-09
S1 | Run search |  |  | 2019-03-07 | 2019-03-06
S2 | Screening abstracts |  |  | 2019-01-02 | 2019-01-01
S3 | Resolve discrepancy |  |  | 2019-01-03 | 2019-01-02
S4 | Obtain full papers |  |  | 2019-01-04 | 2019-01-03
S5 | Arrange for translations of papers |  |  | 2019-01-05 | 2019-01-04
S6 | Screen full papers |  |  | 2019-01-06 | 2019-01-05
S7 | Screen full papers |  |  | 2019-01-07 | 2019-01-06
S8 | Resolve discprepancy - methodological |  |  | 2019-01-08 | 2019-01-07
S9 | Resolve discprepancy - clinical |  |  | 2019-01-09 | 2019-01-08
S10 | Confim list of included papers |  |  | 2019-01-10 | 2019-01-09
REVIEW 1 |  |  |  | 2019-06-03 | 2020-01-30
Seach and screen |  | Time(weeks) | 5 | 2019-06-03 | 2019-07-08
S1 | Run search |  | 5 | 2019-06-03 | 2019-06-09
S2 | Screening abstracts |  | 3 | 2019-06-10 | 2019-06-12
S3 | Resolve discrepancy |  | 3 | 2019-06-13 | 2019-06-17
S4 | Obtain full papers |  | 5 | 2019-06-18 | 2019-06-24
S5 | Arrange for translations of papers |  | 15 | 2019-06-18 | 2019-07-08
S6 | Screen full papers 1 |  | 5 | 2019-06-19 | 2019-06-25
S7 | Screen full papers 2 |  | 5 | 2019-06-19 | 2019-06-25
S8 | Resolve discprepancy - methodological |  | 5 | 2019-06-25 | 2019-07-01
S9 | Resolve discprepancy - clinical |  | 5 | 2019-06-25 | 2019-07-01
S10 | Confirm list of included papers |  | 5 | 2019-07-02 | 2019-07-08
Data extraction and analysis |  | Time(weeks) | 8 | 2019-06-25 | 2019-08-20
D1 | Data extraction 1 |  | 15 | 2019-06-25 | 2019-07-15
D2 | Data extraction 2 |  | 15 | 2019-06-25 | 2019-07-15
D3 | Resolve discprepancy - methodological |  | 10 | 2019-07-16 | 2019-07-29
D4 | Resolve discprepancy - clinical |  | 10 | 2019-07-16 | 2019-07-29
D5 | Data extraction - finalised and merged |  | 10 | 2019-07-16 | 2019-07-29
D6 | Data entry into RevMan |  | 5 | 2019-07-30 | 2019-08-05
D7 | Analysis |  | 5 | 2019-08-06 | 2019-08-12
D8 | Analysis check |  | 5 | 2019-08-13 | 2019-08-19
D9 | Doing SOF |  | 5 | 2019-08-13 | 2019-08-19
D10/T1 | TELECON (ALL) - Agree on analysis, intepretation and key points |  | 1 | 2019-08-20 | 2019-08-20
Write up |  | Time(weeks) | 9.7143 | 2019-07-30 | 2019-10-06
W1 | Write up - ROB, included studies |  | 5 | 2019-07-30 | 2019-08-05
W2 | Write up - Effects of intervention, Research implications, Abstracts, PLS |  | 5 | 2019-08-20 | 2019-08-26
W3 | Write up - Discussions, Implications for practice |  | 5 | 2019-08-27 | 2019-09-02
W4 | Review first drafts and putting together initial draft |  | 5 | 2019-09-03 | 2019-09-09
W5 | Cirulate drafts - comments and feedback | AT | 5 | 2019-09-10 | 2019-09-16
W6 | Review/summarise comments |  | 3 | 2019-09-17 | 2019-09-19
W7/T2 | TELECON (ALL) - Discussions of draft | AT | 1 | 2019-09-20 | 2019-09-22
W8 | Revise drafts |  | 5 | 2019-09-23 | 2019-09-29
W9 | Cirulate drafts - comments and feedback |  | 5 | 2019-09-30 | 2019-10-06
W10 | Revise drafts |  | 5 | 2019-09-30 | 2019-10-06
Peer reviewing |  | Time(weeks) | 10.2857 | 2019-09-30 | 2019-12-11
PR1 | Submit for external peer review |  | 2 | 2019-09-30 | 2019-10-01
PR2 | External Peer review | CRG | 15 | 2019-10-02 | 2019-10-22
PR3 | Review comments and respond to peer reviewers |  | 7 | 2019-10-23 | 2019-10-31
PR4 | Review comments and respond to peer reviewers (clinical) |  | 7 | 2019-11-01 | 2019-11-11
PR5/T3 | TELECON (ALL) - Peer review comments |  | 1 | 2019-11-12 | 2019-11-12
PR6 | Finalise and resubmit for editorial approval |  | 5 | 2019-11-13 | 2019-11-19
PR7 | Editorial review | CRG | 10 | 2019-11-20 | 2019-12-03
PR8 | Review comments and respond to editors |  | 5 | 2019-12-04 | 2019-12-10
PR9 | Review comments and respond to editors (clinical) |  | 5 | 2019-12-04 | 2019-12-10
PR10/T4 | TELECON (ALL) - Editorial comments | AT | 1 | 2019-12-11 | 2019-12-11
Editorial process and publications |  | Time(weeks) | 7 | 2019-12-12 | 2020-01-30
E1 | Submission of final draft |  | 2 | 2019-12-12 | 2019-12-15
E2 | Copy editing of final draft | CRG | 10 | 2019-12-16 | 2019-12-29
E3 | Editorial sign off | CRG | 5 | 2019-12-30 | 2020-01-05
E4 | CEU screening | CRG | 14 | 2020-01-06 | 2020-01-23
E5 | Publication | CRG | 5 | 2020-01-24 | 2020-01-30
Formulas:
Start date = [Finish date, row above]+1
Start date = [Start date, row above]
Finish date = WORKDAY([Start date],[Duration],'Leave dates'!$A5:H65)-1
Finish date = WORKDAY([Start date],[Duration],'[1]Leave dates'!$A2:F60)-1

## Leave dates
This is optional - if this is filled in, Gantt chart will take these dates as off dates without progress. Only fill in if the leave can affect progress (e.g. for weeks)
Public holidays | A1 | A2 | CA1 | CA2 | A3 | A4
2019-04-19 | 2019-02-01
2019-04-22 | 2019-01-02
2019-05-06 | 2019-01-03
2019-05-27 | 2019-01-04
2019-01-05
2019-01-06
2019-01-07
2019-01-08

## TEMPLATE
Task ID | Task | Responsible | Duration | Start date | Finish date | Status | 2019-01-01 | [30 empty] | 2019-02-01 | [27 empty] | 2019-03-01 | [30 empty] | 2019-04-01 | [29 empty] | 2019-05-01 | [30 empty] | 2019-06-01 | [29 empty] | 2019-07-01 | [30 empty] | 2019-08-01 | [30 empty] | 2019-09-01 | [29 empty] | october | [30 empty] | 2019-11-01 | [29 empty] | 2019-12-01
 | time axis 2019-01-01 to 2019-12-31
Review Title | time axis 2019-01-01 to 2019-12-31
| Start date protocol | 2019-01-01
| End date Protocol | 2019-07-01
| Start date review | 2019-06-03
| End date Review | 2020-01-30
Leave planning - for dates authors are unavailable, on leave or away, mark "X" on the affected dates
First author (A1) | bar: 2019-01-01 to 2019-01-08
2nd author (A2) on leave/ not available
Clinical author1 (CA1) on leave/ not available
Clinical author2 (CA2) on leave/ not available
PROTOCOL (abbreviated version) |  |  |  | 2019-01-01 | 2019-07-01
Started
P | TELECON (ALL) - Initial scope of review(s) | AT | 1 | 2019-01-01 | 2019-01-08
P | Scoping PICO & analysis methods |  | 10 | 2019-01-09 | 2019-01-22
P | Confirmation PICO |  | 3 | 2019-01-23 | 2019-01-27
P | Drafting Protocol |  | 4 | 2019-01-23 | 2019-01-28
P | Initial Draft circulated |  | 1 | 2019-01-29 | 2019-01-29
P | Comments/feedback on initial draft |  | 5 | 2019-01-30 | 2019-02-05
P | TELECON (ALL) - Discussions of protocol | AT | 1 | 2019-02-06 | 2019-02-06
P | Revise draft protocol |  | 5 | 2019-02-07 | 2019-02-13
P | Circulate and comment on revised draft |  | 10 | 2019-02-14 | 2019-02-27
P | Final draft agreed |  | 5 | 2019-02-28 | 2019-03-06
P | Data extraction forms finalised |  | 5 | 2019-02-28 | 2019-03-06
P | Submit to Editorial group | FA | 1 | 2019-03-07 | 2019-03-07
P | Copy editing | CRG | 5 | 2019-03-08 | 2019-03-14
P | Initial Editorial feedback |  | 2 | 2019-03-15 | 2019-03-18
P | Edit and resubmit |  | 5 | 2019-03-19 | 2019-03-25
P | Submit for external peer review | CRG | 15 | 2019-03-26 | 2019-04-15
P | External Peer review |  | 5 | 2019-04-16 | 2019-04-24
P | Review comments and respond to peer reviewers |  | 5 | 2019-04-25 | 2019-05-01
P | Review comments and respond to peer reviewers (clinical) |  | 5 | 2019-04-25 | 2019-05-01
P | TELECON (ALL) - Peer review comments | AT | 1 | 2019-05-02 | 2019-05-02
P | Finalise and resubmit for editorial approval | FA | 3 | 2019-05-03 | 2019-05-08
P | Editorial review | CRG | 10 | 2019-05-09 | 2019-05-22
P | Review comments and respond to editors | AT | 5 | 2019-05-23 | 2019-05-30
P | Final submssion | AT | 2 | 2019-05-31 | 2019-06-03
P | Final copy editing & editorial process | CRG | 5 | 2019-06-04 | 2019-06-10
P | Publish | CRG | 15 | 2019-06-11 | 2019-07-01
134
ALL REVIEWS (IF doing a series of reviews)
Search and screen |  |  |  | 2019-03-07 | 2019-01-09
S1 | Run search |  |  | 2019-03-07 | 2019-03-06
S2 | Screening abstracts |  |  | 2019-01-02 | 2019-01-01
S3 | Resolve discrepancy |  |  | 2019-01-03 | 2019-01-02
S4 | Obtain full papers |  |  | 2019-01-04 | 2019-01-03
S5 | Arrange for translations of papers |  |  | 2019-01-05 | 2019-01-04
S6 | Screen full papers |  |  | 2019-01-06 | 2019-01-05
S7 | Screen full papers |  |  | 2019-01-07 | 2019-01-06
S8 | Resolve discprepancy - methodological |  |  | 2019-01-08 | 2019-01-07
S9 | Resolve discprepancy - clinical |  |  | 2019-01-09 | 2019-01-08
S10 | Confim list of included papers |  |  | 2019-01-10 | 2019-01-09
REVIEW 1 |  |  |  | 2019-06-03 | 2020-01-30
Seach and screen |  | Time(weeks) | 5 | 2019-06-03 | 2019-07-08
S1 | Run search |  | 5 | 2019-06-03 | 2019-06-09
S2 | Screening abstracts |  | 3 | 2019-06-10 | 2019-06-12
S3 | Resolve discrepancy |  | 3 | 2019-06-13 | 2019-06-17
S4 | Obtain full papers |  | 5 | 2019-06-18 | 2019-06-24
S5 | Arrange for translations of papers |  | 15 | 2019-06-18 | 2019-07-08
S6 | Screen full papers 1 |  | 5 | 2019-06-19 | 2019-06-25
S7 | Screen full papers 2 |  | 5 | 2019-06-19 | 2019-06-25
S8 | Resolve discprepancy - methodological |  | 5 | 2019-06-25 | 2019-07-01
S9 | Resolve discprepancy - clinical |  | 5 | 2019-06-25 | 2019-07-01
S10 | Confirm list of included papers |  | 5 | 2019-07-02 | 2019-07-08
Data extraction and analysis |  | Time(weeks) | 8 | 2019-06-25 | 2019-08-20
D1 | Data extraction 1 |  | 15 | 2019-06-25 | 2019-07-15
D2 | Data extraction 2 |  | 15 | 2019-06-25 | 2019-07-15
D3 | Resolve discprepancy - methodological |  | 10 | 2019-07-16 | 2019-07-29
D4 | Resolve discprepancy - clinical |  | 10 | 2019-07-16 | 2019-07-29
D5 | Data extraction - finalised and merged |  | 10 | 2019-07-16 | 2019-07-29
D6 | Data entry into RevMan |  | 5 | 2019-07-30 | 2019-08-05
D7 | Analysis |  | 5 | 2019-08-06 | 2019-08-12
D8 | Analysis check |  | 5 | 2019-08-13 | 2019-08-19
D9 | Doing SOF |  | 5 | 2019-08-13 | 2019-08-19
D10/T1 | TELECON (ALL) - Agree on analysis, intepretation and key points |  | 1 | 2019-08-20 | 2019-08-20
Write up |  | Time(weeks) | 9.7143 | 2019-07-30 | 2019-10-06
W1 | Write up - ROB, included studies |  | 5 | 2019-07-30 | 2019-08-05
W2 | Write up - Effects of intervention, Research implications, Abstracts, PLS |  | 5 | 2019-08-20 | 2019-08-26
W3 | Write up - Discussions, Implications for practice |  | 5 | 2019-08-27 | 2019-09-02
W4 | Review first drafts and putting together initial draft |  | 5 | 2019-09-03 | 2019-09-09
W5 | Cirulate drafts - comments and feedback | AT | 5 | 2019-09-10 | 2019-09-16
W6 | Review/summarise comments |  | 3 | 2019-09-17 | 2019-09-19
W7/T2 | TELECON (ALL) - Discussions of draft | AT | 1 | 2019-09-20 | 2019-09-22
W8 | Revise drafts |  | 5 | 2019-09-23 | 2019-09-29
W9 | Cirulate drafts - comments and feedback |  | 5 | 2019-09-30 | 2019-10-06
W10 | Revise drafts |  | 5 | 2019-09-30 | 2019-10-06
Peer reviewing |  | Time(weeks) | 10.2857 | 2019-09-30 | 2019-12-11
PR1 | Submit for external peer review |  | 2 | 2019-09-30 | 2019-10-01
PR2 | External Peer review | CRG | 15 | 2019-10-02 | 2019-10-22
PR3 | Review comments and respond to peer reviewers |  | 7 | 2019-10-23 | 2019-10-31
PR4 | Review comments and respond to peer reviewers (clinical) |  | 7 | 2019-11-01 | 2019-11-11
PR5/T3 | TELECON (ALL) - Peer review comments |  | 1 | 2019-11-12 | 2019-11-12
PR6 | Finalise and resubmit for editorial approval |  | 5 | 2019-11-13 | 2019-11-19
PR7 | Editorial review | CRG | 10 | 2019-11-20 | 2019-12-03
PR8 | Review comments and respond to editors |  | 5 | 2019-12-04 | 2019-12-10
PR9 | Review comments and respond to editors (clinical) |  | 5 | 2019-12-04 | 2019-12-10
PR10/T4 | TELECON (ALL) - Editorial comments | AT | 1 | 2019-12-11 | 2019-12-11
Editorial process and publications |  | Time(weeks) | 7 | 2019-12-12 | 2020-01-30
E1 | Submission of final draft |  | 2 | 2019-12-12 | 2019-12-15
E2 | Copy editing of final draft | CRG | 10 | 2019-12-16 | 2019-12-29
E3 | Editorial sign off | CRG | 5 | 2019-12-30 | 2020-01-05
E4 | CEU screening | CRG | 14 | 2020-01-06 | 2020-01-23
E5 | Publication | CRG | 5 | 2020-01-24 | 2020-01-30